Item P-401 Plant Hot Mix Asphalt Pavement

Special Provision

Description: For rural projects where the designer elects to require minimum production standards.

Date of master being modified: 5/09

Author: Phil N.

Date: 5/1/09

Notes: Requested by Newt Bingham, this special is used on remote projects where a contractor might try to mobilize a small plant with low production capability. There is concern that a small plant would provide an inferior product. This special is probably not necessary on urban projects where economics would deter a contractor from using a small plant.

401-4.10 TRANSPORTING, PLACING, AND FINISHING. Provide capability to consistently produce and pave at a minimum rate of 200 tons per hour. The hot mix asphalt shall be transported from the mixing plant to the site in vehicles conforming to the requirements of Subsection 401-4.3. Deliveries shall be scheduled so that placing and compacting of hot mix asphalt is uniform with minimum stopping and starting of the paver. Adequate artificial lighting shall be provided for night placements. Hauling over freshly placed hot mix asphalt will not be permitted until it has been compacted, as specified, and allowed to cool to ambient temperature. The Contractor may elect to use a material transfer vehicle to deliver hot mix asphalt to the paver.

Item P-401 Plant Hot Mix Asphalt Pavement

Special Provision

Description: For projects that have more than 500 tons of asphalt cement in the bid schedule under pay items P-310b, P-401c, P-602a, P-603a, P-609a, and P-626c collectively.

Date of master being modified: 5/09

Author: Gary Eddy

Date: 11/27/12

Notes: This is Statewide Special Provision A17 effective 7/13/09 (received 7/2/09) with the addition of a sentence to the 1st paragraph by Central Region which says, “The terms asphalt material and asphalt cement are used interchangeably as they apply to the asphalt material price adjustment”.

The Asphalt Material Price Adjustment may result in extra compensation to the Contractor or a savings to the Department when the market price of oil fluctuates dramatically.

If Sections P-310, P-602, P-603, P-609, or P-626 are included in the bid package, add a special provision to each applicable Basis of Payment subsection that points to subsection P-401-9.1 Asphalt Material Price Adjustment.

To date, FAA has not participated in this cost but Headquarters has identified State GF Match funds that will be used to cover the contingency, if necessary, for the price adjustment clause in the Department’s paving projects.

Add the Asphalt Material Price Adjustment item as a contingent sum bid item.  Check with spec writer (Jeanne Lematta) for the amount to use and identify it as non-AIP eligible. We will indicate “GF Match Funds” on our financial status summary and in our Transmittals to Construction memorandum.

401-9.1 ASPHALT MATERIAL PRICE ADJUSTMENT. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount. The terms “asphalt material” and “asphalt cement” are used interchangeably as they apply to the asphalt material price adjustment.

1.	This provision shall apply to asphalt material meeting the criteria of Section 401-2.3, and is included in items listed in the bid schedule of Sections P-310, P-602, P-603, P-609, and P-626.

2.	This provision shall only apply to cost changes in asphalt material that occur between the first Friday of the month of which the bid opening occurs and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	There is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	As used in this subsection, the AAMPI is calculated bi-monthly on the first and third Friday of each month, and is in effect from the day of calculation until the next bi-monthly calculation. The AAMPI is posted on the Department’s Statewide Materials website and is calculated according to the formula posted there. Posting of new AAMPI values after the first and third Friday of each month is typically delayed one to several days. Any delay in the Department’s posting of an updated AAMPI value shall not constitute grounds for using any value other than the value in effect as described in this specification.

5.	Price adjustment will be cumulative and calculated with each progress payment.

For projects where asphalt material is purchased from a commercial plant serving multiple customers, use the AAMPI in effect on the last day of the pay period to calculate price adjustment for asphalt material incorporated into the project during that pay period. For projects where the asphalt material is purchased in advance of incorporating it into the project, use the AAMPI in effect on the last day of the pay period when the asphalt material was purchased. Submit the asphalt material purchase invoice, showing the date purchased, to the Engineer to identify the pay period when the asphalt material was purchased. The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract  = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the Bi-monthly AAMPI in effect on the last day of the pay period, in dollars per ton

6.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

7.	Basis of payment is:

Item P-401e Asphalt Material Price Adjustment		Contingent Sum