Jasper Elementary School  Implementation Management Tool

building  Plan						5/27/10							    	IRN # 029991

| Smart Goals |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal 1: Student Performance Content Area: Reading |  |  |  |  |  |  |  |  |  |
| Goal 1: By 2012, all students in grades k-12 will improve performance on the OAT (grades 3-8 / ogt (grade 10) and local assessments by 5% each year in reading. |  |  |  |  |  |  |  |  |  |
| Strategies, Indicators and Progress Measures |  |  |  |  |  |  |  |  |  |
| Strategy b: implement research based strategies in grades k-12 across all content areas to improve reading comprehension. |  |  |  |  |  |  |  |  |  |
|  | Baseline Measure | Progress Measure |  | Progress Measure |  | Progress Measure |  | Progress Measure |  |
| ### Adult Implementation Indicator | May 2009 | Dec. 2009 | Actual Results | March 2010 | Actual Results | May 2010 | Actual Results | Dec. 2010 | Actual Results |
| 100% of the administration and faculty will apply research based strategies to inform instruction | K-3 0% | K-3 25% |  | K-3 50% |  | K-3 75% |  | K-3 100% |  |
| ### Student Performance Indicator |  |  |  |  |  |  |  |  |  |
| After participating in a classroom using researched based strategies, 100% of students will reach proficiency on district assessments. | K-3 0% | K-3 25% |  | K-3 50% |  | K-3 75% |  | K-3 100% |  |

Implementation Details

| Action Steps | Monitoring Evidence/Data Sources | Person(s) Responsible/ Group(s) | Implementation Timeline |  |  |  | Resources Needed: Budget/Material/ Technology |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2009 | 2010 | 2011 | 2012 |  |
| 1.b.1 Provide common HQPD on research based strategies on reading skills. | Sign in Sheets Agendas | BLT |  | Aug. | May |  | Time/Waiver Day/PD Provider |
| 1.b.2 Plan and provide training and conduct classroom walk- through to ensure that Researched Based Strategies are being used. | Sign in sheets, agendas, Observation and walk through data | Principal/Trained staff/ESC |  | Aug.. | May |  | Time/PD Training/Necessary Materials |
| 1.b.3 A system of observations will be established and implemented to support teachers’ methods of instruction using the information as a discussion point of improvement. | Observation Notes | Principal/BLT |  | Aug. | Ongoing |  | Time |
| 1.b.4 Analyze data and provide feedback from classroom observations pertaining to the use of research based strategies. | Data Conference Notes | Principal/Trained staff/ESC |  |  | Jan. thru June |  | Time/Data Tools |
| 1.b.5. Established Collaborative Teams (CTs) will examine gaps in vertical alignment to establish and implement curricular guides. | Curricular Guides | CT |  | Sept. | June |  | Time/ K-3 Curricular Guides |