Middleborough Public Schools

District Literacy Action Plan

Developed by: Middleborough District Literacy Action Team

Date:  Revised February 2015

@BoroughLiteracy

#ReadWriteYourDestiny

- District Literacy Improvement Goals

- Data Use/Assessment: Establish a district-wide assessment framework.

- Standards-based Curriculum: Align district-wide curriculum to ensure 100% of our students reach proficiency on English language arts MCAS/PARCC in all tested grade levels. Rationale: Currently, the district is at 65% proficiency in ELA.

- Tiered System of Instruction and Intervention: Establish a district- wide system of tiered student support for literacy.

- Family and Community Involvement: Establish meaningful and purposeful academic opportunities in literacy to engage families and community members.

- Action Plan Maps

| 1) Goal Statement | Data Use/Assessment: Establish a district-wide assessment framework. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Action Step 1 | Action Step 2 | Action Step 3 |
|  Action Step |  | Identify common writing assessments at each grade level/course that reflect standards. | Design standards-based writing rubrics at each grade level that can be used to report progress of students toward proficiency. | Reestablish a District Data Team. |
| 1. Timeline |  | 9/1/13 – 6/30/15 | 9/1/14 – 6/30/15 | 9/1/13 – 9/1/15 |
| 2. Lead Person(s) |  | Curriculum Directors & Coordinators, Principals Department Leaders | Curriculum Directors & Coordinators | Curriculum Directors & Coordinators, Literacy Team Subgroup |
| 3. Resources Needed |  | • Teams at each level – elementary, middle school, high school – to identify/develop grade level/course common assessments. • Schools will determine available times. •Possible grant funding | • Form a team that represents all grade levels to recommend assessments. • Schedule of meeting dates and times. • Information regarding DDM development. | • School-level data teams that provide representation to the District Data Team • Schedule of meeting dates and times |
| 4. Specifics of Implementation |  | • Identify/develop writing assessments at elementary schools aligned with standards to collect and use data. • Identify/develop aligned middle school and high school content writing assessments to collect and use data. • Pilot assessments. | • Work in grade-level teams to revise standards-based writing rubrics based on exemplars from other school districts. | • Invite staff members to join the District Data Team. • Review the original materials with course attendees. • Share cycle of inquiry with other members • Establish norms, meeting dates, charge. |
| 5. Measure of Success |  | • Assessment data collected once each trimester/semester. • District data team will review assessment results and report findings. | • Rubrics identified. • Teacher implementation of rubrics. • Teacher participation in calibration of rubric and looking at student work utilizing student work protocols. | • District Data Team • School Level Data Teams |
| 6. Check in/review date |  | 9/8 /14, 1/12/15, May | 9/8/14, 1/12/15, March 2015, May 2015 | 9/8/14, 1/12/15, February 2015, April 2015, May 2015 |

| 2) Goal Statement | Standards-based Curriculum: Align district-wide curriculum to ensure 100% of our students reach proficiency on English language arts MCAS/PARCC in all tested grade levels. Rationale: Currently, the district is at 65% proficiency in ELA. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Action Step 1 | Action Step 2 | Action Step 3 |
|  Action Step |  | • Continue grade level teams PK-8 to design UbD-structured, standards-aligned units of study. • HS will continue to develop common, standards-aligned units of study. | Develop horizontally and vertically aligned curriculum maps. | Implement the utilization of Standards-based IEPs throughout the district. |
| 1. Timeline |  | 9/1/13 -6/30/15 | Elementary: 9/1/15 Secondary: 9/1/16 | 3/19/15-6/30/15 |
| 2. Lead Person(s) |  | Curriculum Directors & Coordinators, Elementary Instructional Coaches; Elementary Curriculum Teams MS/HS Department Leaders | Curriculum Directors & Coordinators, Elementary Instructional Coaches, Department Leaders | Director of Pupil Personnel Services, Curriculum Directors and Coordinators |
| 3. Resources Needed |  | • Use 738 Literacy Partnership Grant Funds to provide time for further unit development. | •Review and revise, as needed, existing curriculum maps. | - Training related to writing and assessing standards-based goals |
| 4. Specifics of Implementation |  | • Work with grade level teams to develop and revise units. • Work with HS departments (grade level, courses) | Align maps/units vertically | - IEPs randomly reviewed for quality assurance by PPS Facilitators - Updated training quarterly - Development of a PLC for 2015-2016 school year |
| 5. Measure of Success |  | • Revised units of study • Proficiency levels based on performance assessments | Published curriculum maps. | - Development of exemplar IEPs - Enhanced collaboration between special educators and general educators - Proficiency levels based on performance assessments |
| 6. Check in/review date |  | 9/8/14, 1/12/15, March 2015, May 2015 | 9/8/14, 1/12/15, March 2015, May 2015, September 2015, January 2016, May 2016 | 4/1/2015, 5/1/15, 6/1/15 - IEP Reviews during Summer 2015 |

| 3) Goal Statement | Tiered System of Instruction and Intervention: Establish a district-wide system of tiered student support for literacy. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Action Step 1 | Action Step 2 | Action Step 3 |
|  Action Step |  | Establish a district-wide system of tiered student support that includes scheduled time and definition of an intervention block at each school. | Pilot a reading intervention program at Grades PreK-12 Lively Letters (PreK) Read Naturally Live (Grades 1-8) Read 180 (Grades 9-12) | Improve instructional practices for all teachers by creating a full continuum of services. |
| 1. Timeline |  | 9/1/13 – 6/30/16 | 11/1/14-6/30/15 | 11/1/15-6/30/16 |
| 2. Lead Person(s) |  | Principals, Assistant Principals Literacy Team Subgroup HS Scheduling Committee | Elementary Curriculum Coordinator, Principals, Director of Pupil Personnel Services | Director of Pupil Personnel Services, Principals |
| 3. Resources Needed |  | • Members who attended the MA Tiered System of Support /Universal Design for Learning (UDL) Academy • Reading Recovery Training for reading teachers • Training and learning walks with Dr. Deborah Harris related to inclusion and teaching all students • New England Association of Schools and Colleges (NEASC) recommendations • HS Scheduling Committee Time • Recommendations of the Middleborough District Review • Stock of books to include recommended readings lists from MA state Frameworks and other reputable sources to provide student access to appropriate texts | - Lively Letters Staff Training:11/4/14 - Read Naturally Live- 3/12/15 - Read 180- TBD | - Determine Planning Sessions for Extended Year Services (EYS) to determine literacy themes, needed materials and projects for students to address reading, expressive and receptive language, writing, etc. - Dr. Deborah Harris work with teachers grades 1-12 during early release days - Special Ed Teachers - Strategic Instructional Model - RISE Revitalizing Instruction for Students and Educators |
| 4. Specifics of Implementation |  | • Use knowledge gained design tiered system of support at each school. • Investigate MS/HS models that successfully provide tiered supports; refer to NEASC • Report and Middleborough Public Schools District Review. | - Special Education teachers utilize pilot program with students - November Lively Letters training - March early release day Read Naturally Live training - Check-in to provide feedback in April and June - Special Education grants are funding the training and materials for the discussed Reading Intervention Programs | - Instructional modeling consultation - The Special Education EYS Program scheduled July 6-August 13, 2015 (6 Weeks) – 9 am-1pm |
| 5. Measure of Success |  | Establishment and definition of the intervention block at each school/level based on the support of the District-wide system of student support. | - Student data - Teacher feedback - Create a teacher survey regarding the use of each program to determine continued usage in 2015-16 school year - Progress monitoring data | - Student data - Closing Achievement Gap - Discovery Education assessment scores - Development of a comprehensive EYS program focused on literacy development |
| 6. Check in/review date |  | 9/8/14, 1/12/15, March 2015, May 2015, September 2015, January 2016, May 2016 | - May 2015 | - June 2015 - September 2015 - November 2015 |

| 4) Goal Statement | Family and Community Involvement: Establish meaningful and purposeful academic opportunities in literacy to engage families and community members. |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Action Step 1 | Action Step 2 | Action Step 3 |
|  Action Step |  | Establish a collection of “Little Free Library” locations throughout Middleborough. | Research and design a district-wide summer reading program in collaboration with Middleborough Public Library. | Produce a “#ReadWriteYour Destiny Where are you Headed” Literacy Fair to promote reading, writing, research, speaking & listening for students and adults of all ages throughout the Middleborough Community. |
| 1. Timeline |  | 8/27/13 – 6/30/14 | 9/1/14-6/30/15 | 3/1/15-6/30/15 |
| 2. Lead Person(s) |  | Literacy Team Subcommittee, Public Librarian | Literacy Team Summer Reading Subcommittee, Elementary Curriculum Coordinator, Public Librarian, | Director of PPS, Literacy Team Literacy Fair Subcommittee |
| 3. Resources Needed |  | • Community Sponsors to fund the building of the “Little Free Library” Book Boxes • Book donations • Volunteers to manage and maintain book boxes (Stewards) • Volunteers to promote use of Little Free Library network • Collaboration with the Public Library - Permission to setup Little Free Library Book Boxes - Partner with Bristol-Plymouth to build book boxes | • Collaboration of the Public Library •Book study (Summer Reading Subcommittee) Summer Reading: Closing the Rich/Poor Reading Achievement Gap by Richard Allington • Collaboration of the Public Library - Summer Reading Program proposals from members of the Summer Reading Book Study | Collaboration with Community Partners and sponsors |
| 4. Specifics of Implementation |  | - Goal 4 Little Free Library Book Boxes - Contact community businesses and community members for sponsorship of book boxes - Request donation of books of varied reading levels PreK through adult to fill book boxes - Request permission to setup book boxes throughout the community - Request building of book boxes from BP - Charter from Little Free Library - Utilize Little Free Library book plates in recognition of the book donations - Order Little Free Library book box charter signs on each box | - Contact Directors - • Share specifics of Summer Reading program designed by sub-committee with teachers, students and families | - Determine subcommittee - Schedule meeting dates 4/9/15, 5/20/15, - Determine September Date and Location-school? |
| 5. Measure of Success |  | • Book boxes built and setup in designated locations throughout Middleborough. • Volunteer Stewards assigned. | • Summer Reading program established • Participation (student reading log) • Literacy assessment data. | - Increased community understanding of the importance of reading and involvement with the event |
| 6. Check in/review date |  | 11/19/14, 1/12/15, March 2015, May 2015 | 9/8/14, 1/12/15, March 2015, May 2015, September 2015, January 2016, May 2016 | May 18, 2015 |