## TPCRE
PRE SCOPING TOTAL PROJECT COST RANGE ESTIMATE DESIGN-BID-BUILD
1
Project Infomration | SP : |  | Route : |  |  | Complied Estimate Date:
| District: |  | Element ID: |  |  |  | Letting Date:
| Project Maturity: | Is it for 20-year Plan? |  | 2 |  | Is it for HIP - 10-year plan? |  | 1899-12-31 |  | Yes
| Project Length: |  | Project Description: | [6 empty] | No
DIVISION |  |  |  | Base Cost Estimate | Risks and Contingency | Most Likely Cost | Mid-Point of Construction Year Cost | Low Range Cost | High Range Cost
Construction Letting |  |  |  | 100000 | 10000 | 110000 | 121275 | 73000 | 243000
Other Construction Total
| Preconstruction Cost |  |  | 10000 | 1000 | 11000 | 12127.5 | 7000 | 24000
| Post Letting Cost |  |  | 10000 | 1000 | 11000 | 12127.5 | 7000 | 24000
| Post Construction Cost |  |  | 1000 | 100 | 1100 | 1212.75 | 1000 | 2000
| Other Construction Elements |  |  | 21000 | 2100 | 23100 | 25467.75 | 15000 | 51000
CONSTRUCTION TOTAL |  |  |  | 121000 | 12100 | 133100 | 146742.75 | 88000 | 293000
Engineering
| Pre-Letting | (12% of Construction Total) |  |  |  | 0 |  | 0 | 0
| Construction | (8% of Construction Total) |  |  |  | 0 |  | 0 | 0
|  | 12% Pre-Letting 8% Construction rules |  | 24200 | 2420 | 26620 |  | 0 | 0
ENGINEERING TOTAL (20 % of Construction Total) |  |  |  | 24200 | 2420 | 26620 |  | 0 | 0
Right of Way
| Standard Real Estate Purchase |  |  |  |  | 0 |  | 0 | 0
| Relocation Costs |  |  |  |  | 0 |  | 0 | 0
RIGHT OF WAY TOTAL |  |  |  | 0 | 0 | 0 |  | 0 | 0
Total Project Cost Estimate |  |  |  | 145200 | 14520 | 159720 | 173362.75
Total Project Cost Range Estimate | [7 empty] | 88000 | 293000
Reported Rounded Total Project Cost Range Estimate | [7 empty] | 88000 | 300000
|  |  |  | Cumulative Inflation Factor Used | 1.1025
|  |  |  | Mid-Point of Construction year | 2014
Estimator: |  |  |  |  | Approval By:
Project Manager: |  |  |  |  | Print Name:
Title:
Date:

## Contruction Letting Cost Basis
Category | WBS Details | Base Cost Estimate
Project Construction Costs | Make a note for details
Detours and Haul Roads | Make a note for details
Construction Traffic Mgmt | Extraordinary Reinforcement
Incident Management
Const Comm/Public Involvement
Turn-Backs: Before
Landscaping
Environmental Mitigation
Environmental Clean-Up | Make a note for details
Construction Letting Base Cost Estimate |  | 0

## Preconstruction Cost Basis
Category | WBS Details | Base Cost Estimate
Agreements
Utilities | Make a note for details
Muncipal/Local Issues | Make a note for details
Railroad | Make a note for details
Environmental Mitigation
Environmental Clean-Up
Pre-Letting Traffic Mgmt | Enforcement and Incident Mgmt
Preconstruction Base Cost Estimate |  | 0

## Post Letting Cost Basis
Category | WBS Details | Base Cost Estimate
SA/Overruns | Make a note for details
Change Orders | Make a note for details
Incentives | Make a note for details
Construction Traffic Mgmt | Extraordinary Reinforcement
Incident Management
Detours and Haul Roads | Make a note for details
Post Letting Base Cost Estimate |  | 0

## Post Construction Cost Basis
Category | WBS Details | Base Cost Estimate
Turn-Backs: After | Make a note for details
Landscaping | Make a note for details
Post Construction Base Cost Estimate |  | 0

## Engineering Cost Basis
Group | Category | Details | Base Cost Estimate
Pre-Letting | (12% of Construction Total)
Environmental Studies
Internal
External
Predesign/Scoping
Internal
External
Detailed Design
Internal
External
Traffic Management
Internal
External
Comm/Public Involvement
Internal
External
R/W Engineering
Internal
External
Construction | (8% of Construction Total)
Administration
Internal
External
Traffic Management
Internal
External
Engineering Cost Base Estimate |  |  | 0

## ROW Cost Basis
Group | Category | Details | Base Cost Estimate
Standard Real Estate Purchase
| Total Takes | Make a note for details
Partial Takes
Relocation Costs
| Residential | Make a note for details
Engineering Cost Base Estimate |  |  | 0

## Proj. Construction Costs Risks
Risk No. | Risk Description | Status of Risk | Date Risk Identified | Contingency Type | Probability (P) | Linear/ Non-Linear | Contingency Amount | Contingency Amount | Impact (I) | Risk Weight | Overall Risk Rating |  |  |  |  | Risk Management Strategy | Response Action | Last Updated/Comments | Next Review Date
|  | Active |  | Time | 5=Very High (60-99%) | 5 =Very High |  |  | 16 =Very High | [6 empty] | AVOID
|  | Retired |  | Cost | 4=High (40-59%) | 4 =High | Linear |  | 8 =High |  |  | Score |  |  |  | MITIGATE
|  |  |  | Scope | 3=Med (20-39%) | 3 =Med | Nonlinear |  | 4 =Med |  |  | 1 | - | 6 | Low | ACCEPT
|  |  |  | Quality | 2=Low (10-19%) | 2 =Low |  |  | 2 =Low |  |  | 7 | - | 14 | Med | TRANSFER
[5 empty] | 1=Very Low (1-9%) | 1 =Very Low |  |  | 1 =Very Low |  |  | 15 | - | 80 | High
[6 empty] | Linear |  |  | Nonlinear
| MANUAL ENTRY | DROP DOWN | MANUAL ENTRY | DROP DOWN | DROP DOWN | DROP DOWN | MANUAL ENTRY | Hidden | DROP DOWN | AUTO (hidden) | AUTO |  |  |  |  | DROP DOWN | MANUAL ENTRY | MANUAL ENTRY | MANUAL ENTRY
1 | Risk Description | Active | Date | Time | 1=Very Low (1-9%) | Linear | Cost/Time Impact Value | Cost/Time Impact Value | 5 =Very High | 5 | Low |  |  |  |  | AVOID | Response Actions | Status Date & Comments | Date of Next Review
2 | [7 empty] | 0
3 | [7 empty] | 0
4 | [7 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39 | [7 empty] | 0
40 | [7 empty] | 0
41 | [7 empty] | 0
42 | [7 empty] | 0
43 | [7 empty] | 0
44 | [7 empty] | 0
45 | [7 empty] | 0
46 | [7 empty] | 0
47 | [7 empty] | 0
48 | [7 empty] | 0
49 | [7 empty] | 0
50 | [7 empty] | 0
[7 empty] | #DIV/0! | 0 |  | 5
0

## Inflation Factors
INFLATION ADJUSTMENTS
PROJECT COSTS - 2012
| 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
FY 2013-2016 STIP | 2013: 0.05; 2014: 0.05; 2015: 0.04; 2016: 0.05
FY 2017-2022 |  |  |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
CUMULATIVE | 1.05 | 1.1025 | 1.1466 | 1.2039 | 1.2641 | 1.3273 | 1.3937 | 1.4634 | 1.5366 | 1.6134
| 1.05 | 1.1 | 1.15 | 1.2 | 1.26 | 1.33 | 1.39 | 1.46 | 1.54 | 1.61
2011-10-20