## Receipt of Materials
LIST OF OWNER'S MATERIALS ON HAND or ON ORDER CARNDELL SUBSTATION
Job #: 419-821 | [7 empty] | Last Rev: | R0 | 2020-05-29
Delivery times are estimated based on previous projects unless shaded in which case delivery times are quoted from manufacturers.
Item* | Supplier Name and Address | P.O. # | Scheduled Delivery Date |  |  | Catalog Number | Qty | Unit Price | Extended Price | Qty Delivered to Gate
Drawing Code
CN-A1 | Victor Insulators |  | Stock | E5 | INSULATOR, 115kV,550kV BIL, TR286, 5" B.C. | 1720 | 3 | 214.13 | 642.39
CN-A2 | Victor Insulators |  | Stock | E13 | INSULATOR, 15kV,110kV BIL, TR205, 3" B.C. | 1751 | 51 | 1306.16 | 66614.16
CN-A3 | KLUTE |  | 16wks | AFDE | AFDE -115kV A- Frame Deadend Structure (CN-S100) |  | 1 | 21676.67 | 21676.67
CN-A4 | KLUTE |  | 16wks | RS | RS - 15kV Underground Feeder Structure (CN-S390) |  | 4 | 4931.07 | 19724.28
CN-A5 | KLUTE |  | 16wks | LCTPT | LCTPT- 15kV Switch Stand (CN-S370) |  | 1 | 3563.76 | 3563.76
CN-A6 | KLUTE |  | 16wks | DS | DS - 15kV Low Side Distribuition Structure (CN-S380) |  | 1 | 22210.12 | 22210.12
CN-A7 | KLUTE |  | 16wks | OP | OP - Switch platform, 3' x 6' (CN-S403) |  | 3 | 661.44 | 1984.32
CN-A8 | KLUTE |  | 16wks | ANCHOR | ANCHOR BOLTS |  | 1 | 3161.92 | 3161.92
CN-B1 | ROYAL |  | 12-14wks | E7 | SWITCH, GROUP OPERATED, "V" TYPE, 115kV, 350kV BIL, 1200A, VERTICAL MOUNT, SWING HANDLE | AV11512 | 1 | 6096.26 | 6096.26
CN-B2 | ROYAL |  | 12-14wks | E8 | SWITCH, GROUP OPERATED, "V" TYPE, 15kV, 110kV BIL, 1200A, HORIZONTAL MOUNT, SWING HANDLE | AV1512 | 1 | 3315.51 | 3315.51
CN-C1 | HUBBELL |  | 3-4 wks | E11 | SURGE ARRESTER DUAL RATED, TYPE EVP, 115kV, 550kV BIL, 42/71 kV MCOV, 4 HOLE PAD, 10" BOLT CIRCLE W/ SHORTING BAR | EVP907102-3001 | 3 | 1380.81 | 4142.43
CN-C2 | OHIO BRASS |  | 7-8wks | E12 | SURGE ARRESTER, 15kV, 110kV BIL, 8.4kV MCOV 10kV DUTY CYCLE, NUT AND WIRE CLAMP; INSULATED BASE W/ISOLATOR, TYPE OPTIMA PDV-100, W/PROTECTIVE CAP | 213709-7314 | 12 | 33.66 | 403.92
0
CN-D1 | ROYAL |  | 6-8wks | E4 | SWITCH RECLOSER BYPASS, 15kV, 110kV BIL, 600A, PORCLAIN INSULATORS TYPE BT | 13212 | 12 | 644.81 | 7737.72
CN-D2 | ROYAL |  | 6-8wks | E6 | SWITCH HOOKSTICK DISCONNECT 15kV 110kV BIL 600A MIN. | 13004 | 12 | 358.29 | 4299.48
CN-D3 | S&C |  | 8-10wks | E9 | SWITCH FUSED DISCONNECT 15kV, 110kV BIL, SMD-20 (STATION SERVICE) BRONZE / TIN PLATED CONNECTOR FOR #2 SOLID TO 397.5kCMIL ACSR | 192232R3-K | 1 | 1048 | 1048
CN-D4 | S&C |  | 11-13wks | E9A | FUSE UNIT SMU-20, 5E STANDARD SPEED (STA. SERV.) | 612005 | 2 | 142.08 | 284.16
CN-E1 | S&C |  | 18-20wks | E10 | TRANS-RUPTER II, MODEL SE, 115kV (ENERGIZE AT 69kV), 420A, 4,200A INTERRUPTION, W / BYPASS SWITCH, FOUR SELF POWERED PROTECTIVE RELAYS (5A SECONDARY), TEST SWITCH, REMOTE GAS-DENSITY ALARM, 48" PHASE SPACING, 8' PEDESTAL, ANCHOR BOLTS (S-81365-1) INCLUDED | 319016R1-J5-F-H-R-U5-E84 W/AB S-81365-1 | 1 | 51361.28 | 51361.28
CN-F1 | G&W Electric |  | 16wks | E2 | 15.5kV Recloser, Three Phase Recloser, Type Viper-S, 15.5kV, 110kV BIL, 630A continuous, 12.5kV interruption, three epoxy insulated vacuum interrupter modules, one three phase magnetic actuator operator, contact position indicator, three 400/200:1 current transformers, three capacitively coupled voltage sensors, recloser specified at 120VAC, "L" style vacuum interrupter modules, 10 foot AC, control, and voltage sensing cables. Recloser requires 120VAC supplied by user. With recloser substation mounting structure. Beckwith Control | D3676SS1LH00 | 3 | 30899.47 | 92698.41
CN-G1 | ARTECHE |  | 10wks | E15 | TRANSFORMER CURRENT 13.2kV 110kV BIL 600:5A 0.15B-1.8 TYPE CRE-17, COLOR ANSI GREY | 756206120 | 3 | 617.49 | 1852.47
CN-G2 | ARTECHE |  | 10wks | E16 | TRANSFORMER POTENTIAL 13.2kV 110kV BIL 63.5:1 0.3W,X,M,Y, TYPE VRN-17, COLOR ANSI GREY | 757101063 | 3 | 1402.19 | 4206.57
CN-H1 |  |  | on-site | E18 | STATION SERVICE TRANSFORMER 10kVA 7.62kV-120/240V |  | 1 | 1100 | 1100
CN-H2 | VIRGINIA TRANSFORMER |  | Late August | E1 | POWER TRANSFORMER, 10/12.5/14MVA W/LTC 115kVx69kV DELTA - 13.2/7.62kV GRD WYE |  | 1 | 603431 | 603431
0
0
0
0
0
0
0
Above Materials Delivered to: See notes | [7 empty] | Cardnell Substation | 921554.83
NOTES:
1. | NOTES
2. | NOTES
*Item corresponds with item in construction units in contract. The value of these materials will be deducted from payments to the Bidder for completed Construction Units.

## Revisions
Revision No. | Description | Date | By
R0 | Original Issue | 2012-02-20 | JMB
R1 | Release for Bid | 2012-02-29 | JMB
R2 | Add CT and PT to bid list | 2012-03-06 | JMB
R3 | Update material list adding steel & relay panels, add costs | 2012-03-12 | JMB
R4
R5
R6
R7
R8
R9
R10